## Product Catalog
SPORTY SHOES
Product Owner
UserStory ID | Feature/Title | User Story | Story Points
US001 | Create an option to create the users. | As an administrator, I want the option to create user, so that I can set up for the master list of users. | 3
US002 | Create an option to create the products. | As an administrator, I want the option to create products, so that I can set up for the master list of products. | 3
US003 | Create an option to view the users,products accordingly | As an administrator, I want the option to view the users and products by id and also list of users,products. | 5
US004 | Create an option to update the users and products accordingly | As an administrator, I want the option to update the users and products by giving the id. | 5
US005 | Create an option to delete the users or products accoridingly | As an adminstrator, I want the option to delete the user or product when there is no use or requirement. | 3
US006 | Create an option to change or reset the password for admin. | As an administrator, I want to reset or change the password when I want or forget it. | 5
US007 | Create an option to view the purchase report by date. | As an administrator, I want the option to view the purchase report of products by user by date. | 5

## Sprint Planning
LEARNERS ACADEMY
Product Owner
UserStory ID | Story Points | Sprint | Story Points | Story
US001 | Create an option to create the users. | As an administrator, I want the option to create user, so that I can set up for the master list of users. | 3 | 1
US002 | Create an option to create the products. | As an administrator, I want the option to create products, so that I can set up for the master list of products. | 3 | 1
US003 | Create an option to view the users,products accordingly | As an administrator, I want the option to view the users and products by id and also list of users,products. | 5 | 2
US004 | Create an option to update the users and products accordingly | As an administrator, I want the option to update the users and products by giving the id. | 5 | 2
US005 | Create an option to delete the users or products accoridingly | As an adminstrator, I want the option to delete the user or product when there is no use or requirement. | 3 | 2
US006 | Create an option to change or reset the password for admin. | As an administrator, I want to reset or change the password when I want or forget it. | 5 | 3
US007 | Create an option to view the purchase report by date. | As an administrator, I want the option to view the purchase report of products by user by date. | 5 | 4